## External pen test 24
Control # | Risk | Control | Findings/Auditor Results | Remediation Recommendation | Actions Taken | Assigned To | Status | Completion Date | Comments | Update Notes
1 | Low | Private IP Address Disclosure | The organization’s Checkpoint firewall at 20.245.187.172 was found to utilize a SSL certificate with the device’s internal IP address as the hostname, exposing the internal IP address to attackers outside the network. | All internal IP addresses should be masked from outside the network. In the case of the Checkpoint firewall, the manufacturer-provided certificate or an internal certificate with the device’s hostname should be utilized. While it is ideal to not expose the device’s hostname, Checkpoint firewalls expose this information by default. As a result, using the hostname for the SSL certificate will not compromise the organization’s security posture. | This will be decommissioned as a last step of the East/West Migration Project. | Rob | Completed | 2024-06-06 | Remediated - Checkpoint firewalls have been shutdown.

## Internal pen test 24
Control # | Risk | Control | Findings/Auditor Results | Remediation Recommendation | Actions Taken | Assigned To | Status | Completion Date | Comments | Update Notes
1 | Critical | CA Server with Web Enrollment Enabled | It was observed that an Active Directory Certificate Authority (AD CA) server was in use and that Web Enrollment was enabled on the CA. The default configuration of a CA server with Web Enrollment enabled makes it vulnerable to an NTLM relay attacks. An Attacker who can obtain a password hash for a Domain Controller (as was possible with PetitPotam) can pass the hash to gain administrative access on the Domain Controller. | If possible, disable Web Enrollment and force clients to use direct enrollment via DCOM. If it is not possible, it is recommended to harden the AD CA server by enabling the features mentioned in the Microsoft guide below. External Documentation PetitPotam Explained Mitigating NTLM Relay Attacks on AD CS | Steve Lockart to review disabling web enrollment and submit CR to CAB | Steve Lockart | Completed | 2024-06-14 | Going to CAb 6-12
2 | Critical | ADCS Certificate Template with User-Supplied SAN | While the Active Directory Certificate Services (ADCS) configuration was being reviewed, it was observed that multiple templates allowed enrollees to supply a Subject Alternative Name (SAN). By allowing enrollees to supply a SAN, the template could be used by an attacker to forge Kerberos tickets for other domain accounts. This includes highly privileged accounts, such as Domain Admins and domain controllers. | Modify the certificate template so that certificates are issued with a SAN set by Active Directory. This can be accomplished in the Certificate Authority Snap-In in Windows Servers. In the template’s Subject Name field, change “Supply in the request” to “Build from this Active Directory information.” | Export active certificates to confirm which templates are being used. We'll disable templates that aren't used and review the active ones for this setting. It was suggested to leave the "supply in the request" setting for web certificates, then test building authentication certificates with the setting changed to AD. | Steve Lockart | Open | 2024-09-30 | It should be noted that this change has the potential to break Kerberos authentication and should be tested before deploying widely at the organization.
3 | High | Global Administrator Account Without MFA | A Global Administrator account was found without Multi-Factor Authentication (MFA) configured. Once the account’s password was compromised, access was able to be obtained to the organization’s Azure environment with the highest possible access rights (Global Administrator). A Global Administrator account has the rights necessary to modify or create Entra ID users, manage virtual machines in Azure, and access any of the organization’s files in Microsoft 365. | The organization should review the current list of Global Administrator accounts and determine if a lower permissions group could fulfill the current access rights for the account. Any remaining Global Administrator accounts should be configured with MFA, including any service accounts. | This is specific to all Global Admins (i.e. Janine Melnitz) where all GA service accounts need to be reduced away from Global Admin roles which will include CAB approval | Transferred to Steve J. 6-10 | Open | 2024-08-31 | All Human Global accounts have MFA
4 | High | Lack of Separated Global Administrator Accounts | Multiple daily driver user accounts were found to have Global Administrator privileges in the organization’s Azure tenant. | Microsoft recommends unique Global Administrator accounts that are not used for any purpose other than Azure administration. Accounts should not be used for daily driver tasks, especially including email. | All remaining "daily driver" accounts have had their Global Admin role removed. Only SA accounts and some service accounts remain as Global Admins. Service accounts will be addressed separately. | Steve J. | Completed | 2024-04-24 | All remaining "daily driver" accounts have had their Global Admin role removed. Only SA accounts and some service accounts remain as Global Admins. Service accounts will be addressed separately.
5 | High | Domain Synchronized Global Administrator Accounts | Multiple accounts with Global Administrator rights were found to be synchronized from the organization’s Active Directory domain. An attacker with domain administrative privileges in the organization’s Active Directory environment could abuse this access to gain Global Administrator privileges in the organization’s Azure tenant. | All Global Administrator accounts should be cloud-only accounts with no ties to Active Directory. Administrators should be instructed to use a unique password, distinct from any Active Directory accounts. | Accounts created and need to sync azure AD with Secret server 7/1/24 Spoke with Steve and Marco. Will configure and test AZ-SA-account with global admin privileges with Steve this week. If successful, we will move forward with the other GA's in that group. | Anthony | Open | 2024-08-30 | 7/4/24 Created SA-AZ-JaureguiS in Azure. Error syncing groups in Secret Server from AAD. "Error Searching Groups: Authorization_Request Denied". 7/16/24 Met with tech from Delinea. Wasn't able to resolve the issue on the call. I exported the Secret Server system logs for their team to investigate.
6 | High | Administrative and Non-Administrative Account Password Re-Use | Although separation of duties, a common best practice, was found to be in use within the organization, it was discovered that one or more users’ non-administrative accounts and their corresponding administrative accounts were sharing passwords. This defeats the purpose of having separate non-administrative and administrative user accounts. | Users who have separate accounts with specific permission levels should be taught never to use the same password on multiple accounts. | See if Varonis Can help with this | Steve J. | Open | 8/302/24
7 | High | SMB Signing Not Enabled and Enforced | SMB signing was not enabled and enforced on several machines within the organization. When SMB signing is not both enabled and enforced, an attacker can potentially relay a user’s network credentials to networked machines without being forced to provide a source identity and can execute commands on those machines as that user. If the relayed user credentials are administrative, this attack can be very dangerous. | It is recommended that SMB signing be enabled and enforced via Group Policy for all machines within the domain |  | Jeanne/Chris Stacks | Open | Q4/24 | Will start mid July
8 | Medium | Weak Password on Kerberoastable Accounts | One or more domain accounts were found to be susceptible to a “Kerberoast” attack during this test. This attack allows and attacker to request a password hash for an affected account via Microsoft’s implementation of Kerberos, the authentication mechanism that is used by Active Directory. This is not a misconfiguration by the organization, rather a mis-implementation by Microsoft. | Microsoft recommends that organizations know which accounts are susceptible to this attack and that steps be taken to remediate – including ensuring that these accounts are not members of administrative groups, if possible. Passwords for these accounts need also be long and strong. |  | Steve J. | Open | Q3/24
9 | Medium | Legacy Network Protocols in Use | Some legacy protocols were found to be enabled on network hosts. This includes LLMNR, NBT-NS/NetBIOS, and mDNS. These protocols allow for “poisoning” attacks which can result in an attacker obtaining password hashes for user and service accounts. | After testing to ensure that the organization’s applications and services won’t be affected, disable LLMNR, NBT-NS, and mDNS in Group Policy for all hosts within the domain. |  | Scott Lewis | Open | Q3/24 | Scott Lewis to add risk acceptance information with details around network segmentation and peer-to-peer communications.
10 | Low | Kerberos RC4 In Use | During the Kerberoast attack, it was discovered that RC4 hashes were in use. RC4 hashes are relatively fast to crack, requiring approximately the same computational power as NetNTLMv2. | Disable usage of Kerberos DES Encryption in Active Directory. Ideally, AES256 would be the only supported encryption type, but AES128 still provides significant advancement over DES/RC4. |  | Jeanne/Chris Stacks | Open | Q4/24
11 | Low | LM Hashes in Use | When password hashes were dumped from a domain-joined host, multiple accounts were found with LM hashes. LM is a weak hashing algorithm that can be cracked nearly instantly with modern hardware. All domain-joined hosts should have LM disabled in favor of more modern hashing algorithms. | Disable Lan Manager (LM) password storage. This change is unlikely to impact modern systems but does have the potential to impact legacy systems. | Go to this site for more info. https://learn.microsoft.com/en-us/troubleshoot/windows-server/windows-security/prevent-windows-store-lm-hash-password | Jeanne/Chris Stacks | Open | Q4/24